## Transition checklist
Management Transition Checklist
From the day the Board votes to 90 days after the new company starts. Free for Boards — myboardmatch.com
# | Phase | Task | Owner | Due | Done | Why it matters
1 | Before notice | Locate the management agreement and read the termination and notice clauses | Board |  |  | Everything downstream is set by this document, not by anyone's preference.
2 | Before notice | Diarise the notice deadline, working backwards from the renewal date | Board |  |  | Missing the window by a week usually costs a full additional year.
3 | Before notice | Confirm the delivery method and notice address the agreement requires | Board |  |  | An email where certified mail is required is the first thing disputed.
4 | Before notice | Vote at a properly noticed meeting with a quorum, or by unanimous written consent | Board |  |  | An unauthorised notice can be withdrawn by the company and is worth nothing.
5 | Before notice | Record the vote in the minutes, with the resolution text | Secretary |  |  | The minutes are the only durable evidence the Board acted.
6 | Before notice | Have counsel review the notice letter | Counsel |  |  | Cheap now, expensive later.
7 | Notice | Send the notice by the method the agreement requires, and by email as courtesy | President |  |  | The certified copy governs; the email stops the manager hearing it from a vendor.
8 | Notice | Keep the certified mail receipt with the minutes | Secretary |  |  | Proof of delivery is the whole point of certified mail.
9 | Notice | Request written acknowledgement within five business days | President |  |  | Silence is not acceptance, and you want it on the record early.
10 | Notice | Notify homeowners on your schedule, with a short factual statement | Board |  |  | If you do not set the story, a rumour will.
11 | Selecting | Agree the scope of services before you speak to anyone | Board |  |  | A Board without a written scope will be sold four different ones.
12 | Selecting | Send the same RFP to every company, with one deadline | Board |  |  | Different questions produce answers that cannot be compared.
13 | Selecting | Require an ancillary fee schedule as a condition of consideration | Board |  |  | A base fee without one is not a price.
14 | Selecting | Interview the assigned manager, not only the salesperson | Board |  |  | The person selling you the contract rarely manages the community.
15 | Selecting | Score independently before discussing, using the scorecard | All directors |  |  | Group discussion first collapses to whoever spoke first.
16 | Selecting | Compare on three-year total cost, not the monthly fee | Treasurer |  |  | The cheapest headline is frequently not the cheapest contract.
17 | Selecting | Check references, including one association that left them | Board |  |  | How a company describes a client it lost is the most informative answer available.
18 | Selecting | Vote and record the resolution, naming the company and the start date | Board |  |  | The resolution is what the new agreement is executed against.
19 | Contracting | Have counsel review the new agreement before signature | Counsel |  |  | Especially the escalator, the cap, the notice window and the exit costs.
20 | Contracting | Confirm the pricing matches the proposal exactly | Treasurer |  |  | Numbers drift between proposal and contract more often than Boards expect.
21 | Contracting | Confirm the named manager is named in the agreement | Board |  |  | A manager promised verbally can be reassigned the week after signing.
22 | Contracting | Confirm insurance certificates, with the association named | Treasurer |  |  | General liability, errors and omissions, and a fidelity or crime bond.
23 | Contracting | Agree the start date and the overlap, if any | Board |  |  | A gap between companies is where records get lost.
24 | Records | Demand the full records list in writing, with a deadline | President |  |  | Ask once, formally. Informal requests are the ones that go unanswered.
25 | Records | Financial records — GL, bank statements, reconciliations, AP/AR, budget | Treasurer |  |  | Without these the new company cannot produce a correct first month.
26 | Records | Homeowner roster with ownership, contact and assessment status | New manager |  |  | The single most valuable file, and the one most often delivered incomplete.
27 | Records | Governing documents, amendments, recorded instruments, plats and surveys | Secretary |  |  | Enforcement is not possible without the current documents.
28 | Records | Vendor contracts, warranties, insurance policies and claim files | New manager |  |  | An unknown auto-renewing vendor contract is a recurring surprise.
29 | Records | Reserve studies, engineering and inspection reports, permits | Board |  |  | The reserve study drives the budget you are about to approve.
30 | Records | Minutes, notices, ballots and election records | Secretary |  |  | Statutory retention periods apply in most states.
31 | Records | Violation, architectural and collection files, including matters with counsel | New manager |  |  | A collection file dropped mid-process can restart the clock.
32 | Records | Keys, fobs, access codes, alarm codes and system credentials | Board |  |  | Change everything the outgoing company had access to.
33 | Money | Open or retitle accounts in the association's legal name | Treasurer |  |  | Association funds should never sit in an account in the manager's name.
34 | Money | Change banking signatories on the effective date | Treasurer |  |  | Not before, and not weeks after.
35 | Money | Redirect assessment payments and notify homeowners of the new method | New manager |  |  | Payments to the old address are the commonest first-month failure.
36 | Money | Reconcile the final accounting against your own records | Treasurer |  |  | Do not accept the outgoing company's figure without checking it.
37 | Money | Hold the final payment until the records arrive | Treasurer |  |  | It is the only leverage that survives the effective date.
38 | First 30 days | Kickoff meeting with the new manager and the Board | Board |  |  | Set expectations while everyone is still paying attention.
39 | First 30 days | Agree the reporting calendar in writing | Board |  |  | Which day financials arrive, and what is in them.
40 | First 30 days | Walk the property with the new manager | Board |  |  | They will see things you have stopped noticing.
41 | First 30 days | Publish the new contact details to every homeowner | New manager |  |  | Twice, by two channels.
42 | First 30 days | Confirm every vendor has been notified and paid current | New manager |  |  | A vendor who stops showing up is usually a vendor who stopped being paid.
43 | Day 90 review | Compare the first three months' financials against the budget | Treasurer |  |  | Variances in the first quarter are usually onboarding errors, and fixable.
44 | Day 90 review | Check response times against what was committed | Board |  |  | If the commitment was contractual, this is when you enforce it.
45 | Day 90 review | Review any charge that was not in the base fee | Treasurer |  |  | The first quarter is when the ancillary schedule becomes real.
46 | Day 90 review | Ask homeowners, briefly and formally, whether service improved | Board |  |  | Three questions, one page. Do it while the change is still comparable.
47 | Day 90 review | Record the review in the minutes | Secretary |  |  | It is the baseline for every renewal conversation from here.
Tasks complete
This checklist is generic and deliberately over-complete. Delete what does not apply to your association; it is much easier to remove a line than to remember a missing one.
BoardMatch automates the middle of this list — the RFP, the proposals, the comparison, the vote record and the notice letter. Free for Boards. — myboardmatch.com